## Project Schedule
PROJECT SCHEDULE
PROJECT NAME | Speech-To-Text Notes App
PROJECT DELIVERABLE | MVP app + docs (README, demo video, architecture)
SCOPE STATEMENT | Capture mic audio; convert to text (online/offline); UI to record, edit, save, search, filter; export TXT/MD; noise gate & mic meter; settings; tests & error handling.
START DATE | END DATE | OVERALL PROGRESS
2025-09-22 | 2025-11-28 | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | all | 2025-09-22 | 2025-09-23 | 2 | Complete | Define scope, roles, risks
Agree on Objectives | all | 2025-09-24 | 2025-09-26 | 3 | Complete | Finalize MVP and stretch goals
Repo and CI | Cassidy | 2025-09-27 | 2025-09-29 | 3 | Complete | Github, issues, basic checks
Architecture & Data Model | all | 2025-09-30 | 2025-10-04 | 5 | Complete | Modules, storage chema, APIs
MVP Pipeline: record->transcribe->display | all | 2025-10-05 | 2025-10-19 | 15 | Complete | Milestone: First draft by Oct 26
Audio Capture & Buffer | Cassidy | 2025-10-05 | 2025-10-16 | 12 | Complete | sounddevice.InputStream + callback
Noise Gate & Mic Meter | Cassidy | 2025-10-13 | 2025-10-25 | 13 | Complete | Real-time visualization
Real-time Chunking & Partial Text | Nathan | 2025-10-07 | 2025-10-21 | 15 | Complete | 20 ms framex -> 2 s chunks
Offiline Transcription Path | Justin | 2025-10-12 | 2025-10-26 | 15 | Complete | Local model fallback
Error Handling (I/O, internet, accuracy) | Nathan | 2025-10-16 | 2025-10-30 | 15 | Complete | 3 retries/chunk + warnings
UI: Recording Controls | Justin | 2025-10-10 | 2025-10-18 | 9 | Complete | Start/Stop, indicator
UI: Editing & Autosave | Justin | 2025-10-18 | 2025-11-01 | 15 | In Progress | Autosave after 500 ms idle
Storage: Notes + Metadata | Cassidy | 2025-10-18 | 2025-11-01 | 15 | In Progress | Local JSON/DB + audio files
Search & Replace (keywords/phrases) |  | 2025-10-22 | 2025-11-05 | 15 | In Progress | Dictionary for domain words
Filter by Date/Tags | Justin | 2025-10-26 | 2025-11-07 | 13 | In Progress | Tag UI + queries
Export TXT/MD (with metadata) | Justin | 2025-10-30 | 2025-11-08 | 10 | In Progress | Filename from title
Settings (language/model/hotkeys) | Cassidy | 2025-11-30 | 2025-11-11 | 13 | In Progress | Config UI
Unit & Mock Tests | Nathan | 2025-11-02 | 2025-11-15 | 14 | In Progress | File I/O, transcription, mocks
Usability Polish & Accessibility | all | 2025-11-09 | 2025-11-18 | 10 | Not Started | Labels, shortcuts
Docs (README + architecture) | Justin | 2025-11-11 | 2025-11-21 | 11 | Not Started | Screenshots + diagram
Demo Video | all | 2025-11-17 | 2025-11-23 | 7 | Not Started | Walkthrough & results
System Testing | all | 2025-11-18 | 2025-11-25 | 8 | Not Started | End-to-end test matrix
Milestone: Second Draft (Nov 9) | all | 2025-11-05 | 2025-11-09 | 5 | Not Started | Accuracy, error handling, storage
Milestone: Final Draft (Nov 24) | all | 2025-11-20 | 2025-11-24 | 5 | Not Started | Ready to submit
Buffer / Slack | all | 2025-11-24 | 2025-11-28 | 5 | Not Started | Contingency, final fixes